# Advisor Onboarding Checklist

Moving from One Broker-Dealer to Another
(Timeline-Driven | Ops + Tech + Compliance Integrated)

Table of Contents

Section Title										  Page Number

Phase 1: Strategy and Risk Review………………………………………………………………… 3

Phase 2: Pre-Transition Build………………………………………………………………………4

Phase 2A: Product and Service Review……………………………………………………..4

Phase 2B: Equipment……………………………………………………………………... 4

Phase 2C: Marketing……………………………………………………………………... 5

Phase 3: Digital Identity and Communication………………………………………………………6

Phase 4: Access, Credentials & Data Planning…………………………………………………........7

Phase 5: Resignation Day……………………………………………………………………….......7

Phase 6: Client Transition and Repapering…………………………………………………………7

Phase 7: Compliance and Stabilization………………………………………………………….......8

## Appendices………………………………………………………………………………………...9

## PHASE 1: STRATEGY & RISK REVIEW

### Timeline: 3-6 Months Prior

### Workflow

- Review current BD agreement

  - Non-solicit / non-compete

  - Forgivable notes & repayment triggers

  - Sunset clauses

- If purchasing practice:

  - Offer letter

  - Letter of Intent

  - Selling Party attorney review

- Confirm Protocol for Broker Recruiting status

  - See Appendix 1

- Confer with specific recruiter and confirm that the transition team is involved

State Licensing Impact Review

- Identify all states where clients reside

- Compare those states to registrations supported by the new BD / RIA

- Flag states with known approval delays or heightened scrutiny

- Identify states that require:

- Full registration vs notice filing

- Advisory registration triggered by a single client

- Identify clients in states that may not be “Day-1 eligible”

- Establish internal rules for those states (no trading / no advice until approved)

- Align resignation timing and ACAT sequencing to state approval timelines

### Business Structure Decisions

- LPL employment association options

  - Select W-2 vs 1099

  - BD-only vs hybrid RIA

  - Form entity (LLC / S-Corp / DBA)

  - Open business bank accounts (if allowed pre-move)

- OBA confirmations

## PHASE 2: PRE-TRANSITION BUILD

### Timeline: 2-3 Months Prior

## PHASE 2A: PRODUCT & SERVICE REVIEW (CONDENSED)

### Product Inventory & Transition

- Inventory all client products:

  - SMA / UMA / models

  - Fee-based advisory accounts

  - Brokerage products

  - Alternatives

  - Insurance & annuities

- Identify proprietary or unsupported products

  - Flag clients requiring liquidation, replacement, or consent

- See Appendix 2

SMA / Models

- Confirm supported SMA/UMA programs

- Map current models to new platform equivalents

- Identify manager changes or liquidations

- Flag tax-sensitive positions

Advisory (Fee-Based) Accounts

- Confirm advisory platforms, billing method, fee amounts

- Review fee schedules, breakpoints, householding

- Identify pricing or service scope changes

Brokerage, Alts & Insurance

- Confirm product availability

- Identify transfer restrictions (alts, annuities)

- Confirm carrier appointments & servicing rules

  - Change of BD form information for annuity carriers

PHASE 2B: EQUIPMENT

### Technology Architecture (Design First)

- CRM selected & BD-approved

  - Wealthbox set up

- Financial planning software selected

  - Optional services: MoneyGuide, Right Capital, Wealth Vision

  - See Appendix 3

- Clientworks set up

  - Integration with other platforms used

- E-signature platform selected (AdobeSign)

- MyRepChat is REQUIRED for client communications on personal devices

Hardware & Office Equipment

- Advisor & staff DELL laptops/desktops

- Optional:

  - Docking stations, monitors, keyboards, mouses

  - Landlines and extensions

  - Secure internet and backup internet

  - Printers/scanners

    - Set up office printers (contact TGI)

    - Scan to email option

  - Shredding system

Cybersecurity & Access Controls

- Hard-drive encryption

- VPN access - Box.com

PHASE 2C: MARKETING (CONDENSED)

### Advisor Profile & Approvals

- Confirm approved title and role with Managing Partners

- Confirm with Compliance what can be prepared before registration vs. what must wait

- Complete advisor intake form

  - Name, credentials, title, office, direct phone/extension, email, team

  - Single source of truth for website, print and forms

- Collect high-resolution headshot (match current team photos)

- Write or refresh bio; advisor approves before compliance review

### Website, Social & Print

- Build website profile and team directory listing in staging

  - Log compliance submission and publishing trigger

- Add advisor to all Contact Us dropdowns and test form routing

- Add advisor to team photos and group graphics

- Business cards and email signature with required LPL disclosures

- Plan social media launch

  - LinkedIn must be under LPL social media supervision before edits

  - AdvisorStream set up (if sharing client content)

### Client Transition Communications

- Wirehouse only: confirm resignation-day outreach rules with Compliance

- Prepare client transition kit:

  - Personalized announcement brochure (Lighthouse template)

  - Transition letter and email in the advisor’s voice

  - Lighthouse & LPL explainer and client FAQ

  - Wirehouse only: call talking points and objection responses

- Submit all client-facing pieces to compliance and track to approval

### Independent Practices Only

- Confirm business entities, DBAs and registrations

- Plan domain redirects, SEO and updates to old online profiles

- Coordinate email and domain cutover with IT

- Send clients a “what changes, what stays the same” note

### Launch & Follow-Up

- Pre-launch check (Week before):

  - Outsider test: can someone find, contact and understand the advisor?

  - All contact points match the intake form

  - Only final, approved versions in the launch folder

- Document go / no-go; Marketing signs off to Transition Lead

- Day 0 (after Compliance clears registration):

  - Publish profile, directory, Contact Us and form routing; send live test inquiry

  - Publish approved social media updates and team graphics

  - Send advisor the final client transition kit

- Week 1–2: re-check website and contact paths; update FAQ and talking points from client questions

- Day 60: close out transition and move advisor to an ongoing marketing plan

## PHASE 3: DIGITAL IDENTITY & COMMUNICATION

### Timeline: 1 Month Prior

### Email & Domain Setup

- Contact IT consultant (Vincent Facchini)

  - He will handle email encryption

- Set up Microsoft Suite

- Approval of LPL and DBA email

- Mobile email configured (optional)

- Email signatures created with proper disclosure

### Phone Systems

- Select phone system (PolyCom Voiceover IP Phones)

- Set up personal direct lines

- Voicemail set up based on LPL approved greeting

  - See Appendix 4

- Texting policy defined (MyRepChat)

  - See Appendix 5

- Microsoft Teams/Zoom/Webex set up

## PHASE 4: ACCESS, CREDENTIALS & DATA PLANNING

### Timeline: 1-2 Weeks Prior

### Login & Credential Setup

- Confirm all login and credentials are set up properly

  - Connect with Vincent if any issues arise

Data Migration Planning (Protocol-Safe)

- Advisor will work with LPL Transition Team

- Confirm allowable client data

- Map old CRM fields → new CRM

- Decide manual vs assisted migration

## PHASE 5: RESIGNATION DAY

### Timeline: Days 0-2

- Make sure acquired advisor has completed the following steps:

  - Submit written resignation

  - Return firm property

  - Do not remove prohibited data

  - No solicitation until allowed

- Branding of new advisor(s):

  - Requested and approved titles and designations

  - Letterheads

    - Notepads

## PHASE 6: CLIENT TRANSITION & REPAPERING

### Timeline: Post Acquisition/Transition (Week 1)

- Branding of new advisor(s) continued:

  - Send Welcome Gift

    - Obtain shirt size

  - Photographs/Headshots of advisor and staff

  - Business cards

  - Welcome letter sent to clients to announce transition

- Begin client outreach (Protocol-compliant)

- Execute new account paperwork (completed with help of Transition Team)

- Initiate ACATs

- Re-establish:

  - Systematic investments

  - RMDs

  - Bill pay & distributions

  - Annuities

  - Income distributions

- Replace proprietary products

  - Mapping of funds

- Track assets moved vs retained

## PHASE 7: COMPLIANCE & STABILIZATION

### Timeline: 1 Month

- Post-move audits completed

- Fee billing verification

- Supervision expectations confirmed

- Close residual old BD accounts

Not all items may be applicable, complete as necessary and contact your LPL Transition Team with any questions.

Appendices

Appendix 1

## Confirming Protocol for Broker Recruiting Status

## PROTOCOL ELIGIBLE

- Limit client data to Protocol-permitted information only, for example:

  - Client name

  - Address

  - Phone number

  - Email address

  - Account title

- Further investigate and confirm whether this is the information is accepted and/or if there is anything else that is permitted

- Contact clients in accordance with Protocol and document all outreach

## NON-PROTOCOL

- Assume no client data may be taken

- Do not signal or hint at departure

- Review non-solicit / non-compete clauses carefully

- Identify “cool-down” periods if applicable

- Wait until legally permitted to contact clients

- Respond only to client-initiated contact, if allowed

- Avoid targeted solicitation if restricted

- Document all interactions

Appendix 2

Appendix 3

Appendix 4

“You have reached the voicemail of _______ with LPL Financial or enter your DBA name. I am currently away from my desk, but if you leave your name and telephone number, I will return your call at my earliest convenience. As a reminder, please do not leave trading instructions by voicemail as they cannot be accepted. OPTIONAL ADD: For immediate assistance in my absence, you may contact LPL Financials direct client service line at (800) 558-7567. Thank you.”

Appendix 5